## ProductBacklog
PRODUCT BACKLOG
Batch 2018_2019
SPRINT BACKLOG | US ID | BACKLOG ITEM |  |  | PRIORITY | RESPONSIBLE | ESTIMATE DATE | REMARKS
|  | AS A/AN | I WANT TO | SO THAT
1 | SB1/US1 | Developer | Detecting human face | It will detect if the human face is present or not | 1 | HC+RK | 2018-09-04
2 | SB1/US2 | Developer | Use best of algorithms | To detect human face accurately | 1 | HC+RK | 2018-09-08
3 | SB1/US3 | Developer | Feature extraction for matching | Feature will be extracted for comparision | 1 | HC+RK | 2018-09-12
4 | SB1/US4 | Developer | Capturing all the faces | Capturing of face | 1 | HC+RK+GK | 2018-09-14
5 | SB1/US5 | Developer | Recognition of the faces | Recognizing multiple faces | 1 | HC+RK+GK | 2018-09-16
6 | SB1/US6 | Developer | Making it robust by time | Calculating time for making time efficient | 1 | HC+RK+GK | 2018-09-18
7 | SB2/US1 | Developer | Detecting multiple human faces | Multiple faces needed to be reconized in one frame | 2 | HC+RK+GK | 2017-09-25
8 | SB2/US2 | Developer | Identifying and matching captured images from database | It will compare faces | 2 | HC+RK+GK | 2017-09-28
9 | SB2/US3 | Developer | Capturing videos | Video is capture for few minutes | 2 | HC+RK+GK | 2017-10-02
10 | SB2/US4 | Developer | Video meta data extraction | Capturing images from video with time frame | 2 | HC+RK+GK | 2017-10-02
11 | SB2/US5 | Developer | Extracting clear image/face from the video | It will extract clear faces from the video to match with data sets | 2 | HC+RK+GK | 2017-10-02
12 | SB2/US6 | Developer | Matching extracted images from the dataset(using same algos mentioned above) | Match those images | 2 | HC+RK+GK | 2017-10-05
13 | SB2/US7 | Developer | Giving unique id to all the members of dataset | It will be displayed who is present in the class | 2 | HC+RK+GK | 2017-10-07
14 | SB2/US8 | Developer | Displaying of Ids when face from video is matched with dataset | Display of Id and its corresponding informations like name, roll no. | 2 | HC+RK+GK | 2017-10-09
15 | SB3/US1 | Developer | Making of attendence sheet with data base | Where record of present student will be displayed | 3 | HC+RK+GK | 2018-10-16
16 | SB3/US2 | Developer | Work Space | To store face/videos for matching | 3 | HC+RK+GK | 2018-10-18
17 | SB3/US3 | Developer | Desing GUI of the sheet | Designing of sheet | 3 | HC+RK+GK | 2018-10-18
18 | SB3/US4 | Developer | Making class wise databases | For attendence of each section | 3 | HC+RK+GK | 2018-10-18
19 | SB3/US5 | Developer | Connecting GUI with database | conectivity of database with camera | 3 | HC+RK+GK | 2018-10-20
20 | SB3/US6 | Developer | Connecting Video extraction | Output- attendence sheet is ready | 3 | HC+RK+GK | 2018-10-21
21 | SB3/US7 | Developer | List of all subjects | to see attendence of indivisual subjects | 3 | HC+RK+GK | 2018-10-21
22 | SB3/US8 | Developer | Login for indivisual subject attendence | to see result of attendence indivisually | 3 | HC+RK+GK | 2018-10-22
23 | SB3/US9 | Developer | Showing output on database | All attendence is counted in total | 3 | HC+RK+GK | 2018-10-22
24 | SB3/US10 | Developer | Marking of attendence | All attendence is counted in total | 3 | HC+RK+GK | 2018-10-23
25 | SB4/US1 | Developer | Implementation on the hardware | Practical Implimentation | 4 | HC+RK+GK | 2019-01-10
26 | SB4/US2 | Developer | conecting with the camera | Practical Implimentation | 4 | GK+RK | 2019-01-11
27 | SB4/US3 | Developer | Implementing in the college | Real time applicaton implimentation | 4 | GK+RK | 2019-01-12
28 | SB4/US4 | Developer | Track the accuracy and working | Testing on implimented application | 4 | GK+RK | 2019-01-13
29 | SB4/US5 | Developer | Finding issues | Finding problem after implimentation | 4 | GK+RK | 2019-01-13
30 | SB4/US6 | Developer | Resolving issues | Resolving the issue of the found problem | 4 | GK+RK | 2019-01-14
31 | SB4/US7 | Developer | Impleting again | Finally impliment the system | 4 | GK+RK | 2019-01-15
|  | HC | Harshit Chourasiya
|  | GK | Gunjan Kundalia
|  | RK | Ruchi kumari

## SprintBacklog 1
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 1 - AUTOMATIC FACE DETECTION AND RECOGNITION
SB1/US1 | I want to detect human face and it will only recognize human face only | SB1/US1/T1 | Write code for Dectection of human face | HC + GK | In Progress | 2018-04-09
|  | SB1/US1/T2 | Testing of code | HC + GK | In Progress | 2018-04-09
|  | SB1/US1/T3 | Solving the error if any | HC + GK | In Progress | 2018-04-09
SB1/US2 | I will implement multiple algorithms, and algorithm with best results will be used | SB1/US2/T1 | By applying Haar Cascading algorithm | HC + RK | In Progress | 2018-04-09
|  | SB1/US2/T2 | Get the accuracy for haar cascading algorithm | HC + RK | In Progress | 2018-04-09
|  | SB1/US2/T3 | Solving the error if any | HC + RK | In Progress | 2018-04-09
|  | SB1/US2/T4 | By applying LBP (Local binary patterns) algorithm | HC + RK | In Progress | 2018-04-09
|  | SB1/US2/T5 | Get the accuracy for LBP algorithm | HC + RK | In Progress | 2018-04-09
|  | SB1/US2/T6 | Solving the error if any | HC + RK | In Progress | 2018-04-09
|  | SB1/US2/T7 | Compare and seclet the best acuurate algorithm. | HC + RK | In Progress | 2018-04-09
SB1/US3 | Feature extraction algorithms for matching with from dataset | SB1/US3/T1 | Applying algorithm for extracting the features of faces | HC+GK+RK | In Progress | 2018-08-09
|  | SB1/US3/T2 | Solving the error if any | HC+GK+RK | In Progress | 2018-08-09
|  | SB1/US3/T3 | Testing of written algorithm code for extraction | HC+GK+RK | In Progress | 2018-08-09
SB1/US4 | Feature Extraction | SB1/US4/T1 | Applying PCA using Eigen values | HC+GK+RK | In Progress | 2018-12-09
|  | SB1/US4/T2 | Applying PCA using Fisher values | HC+GK+RK | In Progress | 2018-12-09
|  | SB1/US4/T3 | Applying KNN Algorithm | HC+GK+RK | In Progress | 2018-12-09
|  | SB1/US4/T4 | Applying K-means Algorithm | HC+GK+RK | In Progress | 2018-12-09
|  | SB1/US4/T5 | Applying Haar-cascading Alogorithm | HC+GK+RK | In Progress | 2018-12-09
|  | SB1/US4/T6 | Applying Wavelet Transformation | HC+GK+RK | In Progress | 2018-12-09
|  | SB1/US4/T7 | Applying LBP (Local binary patterns) Algorithm | HC+GK+RK | In Progress | 2018-12-09
|  | SB1/US4/T8 | Applying Attribute Selection using Eigen values | HC+GK+RK | In Progress | 2018-12-09
|  | SB1/US4/T9 | Applying Attribute Selection using Fisher values | HC+GK+RK | In Progress | 2018-12-09
|  | SB1/US4/T10 | Obtain accuracy result for all the above algoritms. | HC+GK+RK | In Progress | 2018-12-09
|  | SB1/US4/T11 | Compare accuracy and seclet the best acuurate algorithm. | HC+GK+RK | In Progress | 16/9/2018
SB1/US5 | Faces will be captured and saved temporily to use it for matching with dataset | SB1/US5/T1 | Take the screenshot of the as image | HC + GK + RK | In Progress | 16/9/2018
|  | SB1/US5/T2 | Store that screenshot in database | HC + GK + RK | In Progress | 16/9/2018
|  | SB1/US5/T3 | Provide the unique id to the picture | HC + GK + RK | In Progress | 16/9/2018
|  | SB1/US5/T4 | Similarly capture all the faces detected | HC + GK + RK | In Progress | 16/9/2018
SB1/US6 | Comparision of the faces using multiple algorithms | SB1/US6/T1 | Applying PCA using Eigen values | HC + RK | In Progress | 16/9/2018
|  | SB1/US6/T2 | Applying PCA using Fisher values | HC + RK | In Progress | 16/9/2018
|  | SB1/US6/T3 | Applying K-means Algorithm | HC + RK | In Progress | 16/9/2018
|  | SB1/US6/T4 | Applying Haar-cascading Alogorithm | HC + RK | In Progress | 16/9/2018
|  | SB1/US6/T5 | Applying Wavelet Transformation | HC + RK | In Progress | 16/9/2018
|  | SB1/US6/T6 | Applying LBP (Local binary patterns) Algorithm | HC + RK | In Progress | 16/9/2018
|  | SB1/US6/T7 | Applying Attribute Selection using Eigen values | HC + RK | In Progress | 16/9/2018
|  | SB1/US6/T8 | Applying Attribute Selection using Fisher values | HC + RK | In Progress | 16/9/2018
|  | SB1/US6/T9 | obtain accuracy result for all the above algoritms. | HC + RK | In Progress | 16/9/2018
|  | SB1/US6/T10 | Compare accuracy and seclet the best acuurate algorithm. | HC + RK | In Progress | 18/9/2018
SB1/US7 | Making it robust by time, so that it will become more time efficient and accurate | SB1/US7/T1 | Obtain the accuracy for all algorithm written on the basis of time | HC + GK + RK | In Progress | 18/9/2018
|  | SB1/US7/T2 | Compare the result obtain for all algorithm | HC + GK + RK | In Progress | 18/9/2018
|  | SB1/US7/T3 | Select the best algorithm. | HC + GK + RK | In Progress | 18/9/2018
SB1/US8 | Now algoarithms will be implemented such that it will detect multiple faces altogether | SB1/US8/T1 | Repeat this process upto the last face detection. | HC + GK + RK | In Progress | 18/9/2018
|  | SB1/US8/T2 | Provide the unique id to the detected face. | HC + GK + RK | In Progress | 18/9/2018
|  | HC | Harshit Chourasiya
|  | GK | Gunjan Kundalia
|  | RK | Ruchi kumari

## SB Hours 01
Sprint Backlog 1
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
1 | As a developer I want to develop the hardware so that Wii-mote can be placed on the screen | Search about the hardware setup
Search about components required
Purchase component from Market
Develop the hardware
2 | As a developer I want to search for applications to be developed so that I can identify an application to be developed | Search annotation application
search paint application
search video making application
search audio recording applications
3 | As a developer I want to study about the technology to be used so I can identify the technology for application | Study tutorials
Study tutorials
start with Basics of c#
start with Basics of c#
4 | As a developer I want to begin coding in swings so I can start with designing of the application | start with Basics of c#
start with Basics of c#
|  | coding of onscreen application |  |  |  | 0
|  | coding of onscreen application |  |  |  | 0
5 | As a developer I want to start coding of my application so that I can develop application | coding of onscreen application |  |  |  | 0
|  | coding of onscreen application |  |  |  | 0
Debug the code
Debug the code
6 | As a developer I want to implement my designed application so that I can use it | Implentation of application on virtual screen.
Implentation of application on virtual screen.
Implentation of application on virtual screen.
Implentation of application on virtual screen.
7 | As a developer I will implement the final project in the classrooms so that system can be used by the users at college | Switch on the projector and set the projected screen
Interface it with PC/laptop
Switch on the projector and set the projected screen
Interface it with PC/laptop
8 | As a tester I will check the whole system implemented in classrooms so that final system could be tested | Callibrate WII remote with virtual screen
Use different applications on the virtual screen
Check the changes made at the virtual screen
Checking if it is working effectively with the laptop and not damaged
9 | As a developer I will prepare the final delivarables of the whole system so that I can give the entire system | Prepare all hardware deliverables
Prepare all software deliverables
Prepare a hardware & software guide
Prepare a user manual & guide for the users
10 | As a developer I want to give training to faculty & students so that they can interact with the system & use it | Giving information to users about the project
Project demonstration
Project demonstration
Project to be operated by different users
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch01
Spring Backlog 01 burn down chart
Date | Planned Total Task | Actual Incompleted Task
2018-09-04 | 43 | 43 | Tasks
2018-09-08 | 33 | 36
2018-09-12 | 19 | 24
2018-09-14 | 12 | 19
2018-09-16 | 6 | 11
2018-09-18 | 0 | 7
Days

## SprintBacklog 2
SPRINT BACKLOG 2
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 2 - DATA EXTRACTION FROM VIDEOS
SB2/US1 | I will create dataset of faces beforehand for attendence(database), where attendence will be marked | SB2/US1/T1 | Data set consisting of all the students in a class | GK + RK | NOT STARTED | 25/9/2018
|  | SB2/US1/T2 | Dataset of time table | GK + RK | NOT STARTED | 25/9/2018
SB2/US2 | Identifying and matching captured images from database | SB2/US2/T1 | Assigning Ids to the faces in dataset | HC + GK + RK | NOT STARTED | 25/9/2018
|  | SB2/US2/T2 | Check faces with Ids | HC + GK + RK | NOT STARTED | 25/9/2018
|  | SB2/US2/T3 | If matched than mark attendence | HC + GK + RK | NOT STARTED | 28/9/2018
SB2/US3 | Videos will be captured | SB2/US3/T1 | Making video for span of time | HC + GK + RK | NOT STARTED | 28/9/2018
SB2/US4 | Frames with clearer images will be extracted from the video | SB2/US4/T1 | Fast and robust extraction key method algorithms | HC + GK + RK | NOT STARTED | 2018-02-10
|  | SB2/US4/T2 | Implementing and extracting images | HC + GK + RK | NOT STARTED | 2018-02-10
|  | SB2/US4/T3 | Matching images with dataset | HC + GK + RK | NOT STARTED | 2018-02-10
SB2/US4 | Matching extracted images from the dataset (using same algos mentioned above) | SB2/US5/T1 | Using algorithms | HC + GK | NOT STARTED | 2018-05-10
|  | SB2/US6/T2 | Fast and robust extraction key method | HC + GK | NOT STARTED | 2018-05-10
SB2/US5 | Giving unique id to all the members of dataset and this unique id will be used to mark attendence against them | SB2/US7/T1 | Assigning unique ids to datasets | HC + GK + RK | NOT STARTED | 2018-07-10
|  | SB2/US7/T2 | It will be used to match faces and mark attendence | HC + GK + RK | NOT STARTED | 2018-07-10
SB2/US6 | Displaying of Ids when face from video is matched with dataset | SB2/US8/T1 | Mark if face is matched with ids | HC + GK + RK | NOT STARTED | 2018-09-10
|  | SB2/US8/T2 | Display attendence | HC + GK + RK | NOT STARTED | 2018-09-10
|  | HC | Harshit Chourasiya
|  | GK | Gunjan Kundalia
|  | RK | Ruchi kumari

## SB Hours 02
Sprint Backlog 2
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch02
Spring Backlog 02 burn down chart
Date | Planned Total Task | Actual Uncompleted Task
2017-09-25 | 15 | 15 | Tasks
2017-09-28 | 11 | 12
2017-10-02 | 8 | 9
2017-10-05 | 5 | 7
2017-10-07 | 2 | 5
2017-10-09 | 0 | 3
0
Days

## SprintBacklog 3
SPRINT BACKLOG 3
US ID | USER STORY | TASK ID | TASK ID | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 3 - WORKING ON ATTENDENCE SYSTEMWITH DATABASE AND GUI
SB3\US1 | I will prepare an attendence sheet where attendence will be marked | SB3\US1\T1 | I will prepate a sheet containg datas of students so that I can use it while marking attendence | GK + RK | NOT STARTED | 16/10/2018
|  | SB3\US1\T3 | If the face is recognized and matched attence will be marked in data sheet | GK + RK | NOT STARTED | 16/10/2018
SB3\US2 | I will require work space where images of students will be stored as dataset | SB2\US2\T1 | Workspace will be required to store dataset as images | GK + HC | NOT STARTED | 16/10/2018
|  | SB3\US2\T2 | Database will be connected to datasets | GK + HC | NOT STARTED | 16/10/2018
|  | SB3\US2\T3 | Also I will store temporary images while marking attendence and matching faces | GK + HC | NOT STARTED | 16/10/2018
SB3\US3 | Design GUI of the system | SB3\US3\T1 | User interface will be required so that faculty can login and get attendence | RK + HC | NOT STARTED | 18/10/2018
|  | SB3\US3\T2 | That login page will be secured with user name and password | RK + HC | NOT STARTED | 18/10/2018
SB3\US4 | Making class wise database, which will used for attendence of that particular class | SB3\US4\T1 | There will be a separate sheet for each class so that markings can be seperated | HC+GK | NOT STARTED | 18/10/2018
|  | SB3\US4\T2 | There will also a separate database table for each of the class. | HC+GK | NOT STARTED | 18/10/2018
|  | SB3\US4\T3 | That sheet of the particular class will connect with its database table. | HC+GK | NOT STARTED | 18/10/2018
SB3\US5 | Connecting GUI with the database | SB3\US5\T1 | The designed GUI will connected in database | HC + RK | NOT STARTED | 18/10/2018
SB3\US6 | Connecting vedio extraction | SB3\US6\T1 | System will select the vedio | HC + GK | NOT STARTED | 20/10/2018
|  | SB3\US6\T2 | The perfect snapshot of that vedio will taken by the system | HC + GK | NOT STARTED | 20/10/2018
|  | SB3\US6\T3 | That snapshot/small vedio will connected through the database. | HC + GK | NOT STARTED | 20/10/2018
SB3\US7 | List of all the subjects | SB3\US7\T1 | Create the list of all the subjects along with the faculty name. | HC + GK | NOT STARTED | 21/10/2018
|  | SB3\US7\T2 | Connect that list with database | HC + GK | NOT STARTED | 21/10/2018
|  | SB3\US7\T3 | List will be displayed in database table. | HC + GK | NOT STARTED | 21/10/2018
SB3\US8 | Login for individual subject attendence | SB3\US8\T1 | Login will required for each of the subject | RK + HC | NOT STARTED | 22/10/2018
|  | SB3\US8\T2 | Admin will has right to login every time | RK + HC | NOT STARTED | 22/10/2018
SB3\US9 | Marking of attendence as per lectures | SB3\US9\T1 | Attendence will mark according to matched face in databse | GK+ HC | NOT STARTED | 23/10/2018
|  | SB3\US9\T2 | Marking attendence will display in database table | GK+ HC | NOT STARTED | 23/10/2018
|  | SB3\US9\T3 | A sheet of that attendence will be updated | GK+ HC | NOT STARTED | 23/10/2018
SB3\US10 | Showing output in database | SB3\US10\T1 | A sheet with marked attendence will display in the database. | GK+ HC | NOT STARTED | 23/10/2018
|  | HC | Harshit Chourasiya
|  | GK | Gunjan Kundalia
|  | RK | Ruchi kumari

## SB Hours 03
Sprint Backlog 3
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch03
Spring backlog 3 Burnt Down chart
Date | Planned Total Task | Actual Uncompleted Task
2018-10-16 | 25 | 25 | Tasks
2018-10-18 | 19 | 20
2018-10-20 | 14 | 16
2018-10-21 | 9 | 11
2018-10-22 | 5 | 7
2018-10-23 | 0 | 4
0
Days

## SprintBacklog 4
SPRINT BACKLOG 4
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 4 - HARDWARE IMPLEMENTATION OF SYSTEM
SB4/US1 | I want to implementation the software on the hardware | SB4\US1\T1 | Select a proper hardware apparatuses. | GK + RK | NOT STARTED | 2019-10-01
|  | SB4\US1\T2 | Combine them together as a proper system. | GK + RK | NOT STARTED | 2019-10-01
|  | SB4\US1\T3 | Implement the software on hardware system. | GK+ RK | NOT STARTED | 2019-10-01
SB4/US2 | I want to connect the camera | SB4\US2\T1 | Selection of camera according to their quality and features. | HC + GK + RK | NOT STARTED | 2019-10-01
|  | SB4\US2\T2 | Connect the camera with rerspective devices. | HC + GK + RK | NOT STARTED | 2019-10-01
|  | SB4\US2\T3 | Implement program using camera (testing). | HC + GK + RK | NOT STARTED | 2019-10-01
SB4/US3 | I want to implement this project in the college | SB4\US3\T1 | There will be a proper and final connection between camera and other devices. | HC + GK + RK | NOT STARTED | 2019-11-01
|  | SB4\US3\T2 | The camera get mounted in every classrooms. | HC + GK + RK | NOT STARTED | 2019-11-01
|  | SB4\US3\T3 | Setup of system will be done properly. | HC + GK + RK | NOT STARTED | 2019-11-01
|  | SB4\US3\T4 | Test the whole project as hardware and software system both. | HC + GK + RK | NOT STARTED | 2019-11-01
SB4/US4 | I want to track the accuracy and working | SB4\US4\T1 | Find out whether the system is accurate with their working or not. | HC + GK + RK | NOT STARTED | 2019-12-01
|  | SB4\US4\T2 | Find out whether the system works on time or not. | HC + GK + RK | NOT STARTED | 2019-12-01
|  | SB4\US4\T3 | Find out the time consumed by system. | HC + GK + RK | NOT STARTED | 2019-12-01
SB4/US5 | I will find issues if any one is present there | SB4\US5\T1 | Find out any issue if occurs in the hardware system. | HC + GK + RK | NOT STARTED | 13/1/2019
|  | SB4\US5\T2 | Find out any issue if occurs in the software system. | HC + GK + RK | NOT STARTED | 13/1/2019
|  | SB4\US5\T3 | We will try to catch the errors if any present in their in program. | HC + GK + RK | NOT STARTED | 13/1/2019
|  | SB4\US5\T4 | We will find if any updates are required or not. | HC + GK + RK | NOT STARTED | 13/1/2019
SB4/US6 | I will resolve the issues as per their requirements. | SB4\US6\T1 | Solve the issues related with the hardware system accordingly. | HC + GK + RK | NOT STARTED | 14/1/2019
|  | SB4\US6\T2 | Solve the issues related with the software system accordingly. | HC + GK + RK | NOT STARTED | 14/1/2019
|  | SB4\US6\T3 | Resolve all the errors present in the program. | HC + GK + RK | NOT STARTED | 14/1/2019
|  | SB4\US6\T4 | We will make update according to the requirements of the user. | HC + GK + RK | NOT STARTED | 14/1/2019
SB4/US7 | I will implement system again after modification and testing | SB4\US7\T1 | After making all the modification the system get test again. | HC + GK + RK | NOT STARTED | 15/1/2019
|  | SB4\US7\T2 | After testing the system get set up according to the requirements. | HC + GK + RK | NOT STARTED | 15/1/2019
|  | SB4\US7\T3 | Implementation of the system occurs again. | HC + GK + RK | NOT STARTED | 15/1/2019
|  | HC | Harshit Chourasiya
|  | GK | Gunjan Kundalia
|  | RK | Ruchi kumari

## SB Hours 04
Sprint Backlog 4
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch04
Date | Planned Total Task | Actual Uncompleted Task
2019-01-10 | 24 | 24 | Tasks
2019-01-11 | 18 | 19
2019-01-12 | 13 | 15
2019-01-13 | 9 | 12
2019-01-14 | 5 | 8
2019-01-15 | 0 | 5
0
Days